Department of Human Services

Implementation Plan

For contract consolidation by CBO

March 19, 2003

CBO (Contractor)					Target Date

Asian Perinatal Advocates				July 2003

Catholic Charities					July 2003

Children’s Council of San Francisco			Accomplished

Community Housing Partnership			July 2003

Compass Community Services			July 2003

Episcopal Community Services			July 2003

Hamilton Family Services				July 2003

Larkin Street Youth Services				July 2004

Mission Housing Development Corp			July 2004

Tenderloin Housing Clinic				July 2004

Family Support Services of the Bay Area                  July 2004

Assumptions/variables:

- The effected CBOs will consent to the consolidation.

- Negotiations can be completed for July 2003 start and Commission hearings can be scheduled.

- OCA can expedite the review and certification of the new contracts

- A procedure can be agreed upon regarding Sole Source exemption and renewal of contracts

- Services funded from Non-County sources will be implemented into consolidated contract as they expire or renew.

The back-up plan would be to implement these consolidations no later than October 2003.